## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Introduction to Project | MUST HAVE | No Dependency | Dolendra | 3 - Completed
Sprint 2 | Sprint 2 | US-2 | Workflow Creation and Project Goal Definition | MUST HAVE | Lucidchart | Dolendra | 3 - Completed
Sprint 3 | Sprint 3 | US-3 | Collect customer reviews from multiple platforms (YouTube API) to centralize raw feedback data. | MUST HAVE | YouTube API, Scrapers | Dolendra | 3 - Completed
Sprint 4 | Sprint 4 | US-4 | Clean and preprocess raw review data to remove noise and normalize text. | SHOULD HAVE | OpenAI, Groq Embeddings | Dolendra | 3 - Completed
Sprint 5 | Sprint 5 | US-5 | Database Design (Pinecone Schema and Embedding Collection Setup) | MUST HAVE | Pinecone | Dolendra | 3 - Completed
Sprint 6 | Sprint 6 | US-6 | Implement a LangChain retriever to fetch contextually relevant reviews based on user queries. | SHOULD HAVE | Langchain | Dolendra | 3 - Completed
Sprint 7 | Sprint 7 | US-7 | Content Gap Detection and Improvement Module (Alerts & Reports) | MUST HAVE | Tracker, Usage Logs | Dolendra | 3 - Completed
Sprint 8 | Sprint 8 | US-8 | UI Integration and Query Flow Implementation (React Dashboard + FastAPI) | MUST HAVE | React, FastAPI, Recommendation Engine | Dolendra | 3 - Completed
Sprint 9 | Sprint 9 | US-9 | Final Testing and System Integration with Demo Preparation | MUST HAVE | All previous modules | Dolendra | 3 - Completed
Sprint 10 | Sprint 10 | US-10 | System Deployment (Vercel + Render), CI/CD Setup, Performance Optimization | MUST HAVE | Entire system | Dolendra | 3 - Completed
Sprint 11 | Sprint 11 | US-11 | Full Documentation (Tech Docs, Architecture, API, UI Flow) & User Training | SHOULD HAVE | All previous modules | Dolendra | 3 - Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Priority | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
[9 empty] | 122 | 42 | 34 | 21 | 10 | 4 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
US_1 | T1 | Project Setup and Repository Initialization | 29-Dec-25 | 30-Dec-25 | Dolendra | Planning | Completed | High | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_2 | T2 | Workflow Definition and Requirement Finalization | 30-Dec-25 | 02-Jan-26 | Dolendra | Planning | Completed | High | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_3 | T3 | Architecture Diagram and Module Design | 02-Jan-26 | 05-Jan-26 | Dolendra | Design | Completed | High | 8 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_4 | T4 | YouTube API & Data Ingestion Module | 05-Jan-26 | 10-Jan-26 | Dolendra | Build | Completed | High | 9 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_5 | T5 | Data Cleaning and Preprocessing Pipeline | 10-Jan-26 | 14-Jan-26 | Dolendra | Build | Completed | High | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_6 | T6 | Sentiment and Aspect Tagging / Feature Extraction | 14-Jan-26 | 17-Jan-26 | Dolendra | Build | Completed | High | 10 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_7 | T7 | Embedding Generation using Sentence Transformers | 17-Jan-26 | 20-Jan-26 | Dolendra | Build | Completed | Medium | 8 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_8 | T8 | Pinecone Vector Database Setup and Indexing | 20-Jan-26 | 24-Jan-26 | Dolendra | Build | Completed | High | 8 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_9 | T9 | LangChain Retriever Integration | 24-Jan-26 | 27-Jan-26 | Dolendra | Integration | Completed | High | 10 | 4 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_10 | T10 | RAG Pipeline with Groq LLM Integration | 27-Jan-26 | 01-Feb-26 | Dolendra | Integration | Completed | High | 12 | 3 | 2 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_11 | T11 | FastAPI Backend and React Dashboard UI Development | 01-Feb-26 | 08-Feb-26 | Dolendra | Build | Completed | High | 13 | 4 | 4 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US_12 | T12 | System Testing, Debugging & Performance Fixes | 08-Feb-26 | 12-Feb-26 | Dolendra | Test | Completed | High | 15 | 4 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US_13 | T13 | Final Demo Preparation & Presentation Building | 12-Feb-26 | 14-Feb-26 | Dolendra | Documentation | Completed | Medium | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US_14 | T14 | Documentation (Technical + User Manual) | 14-Feb-26 | 17-Feb-26 | Dolendra | Documentation | Completed | Medium | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
US_15 | T15 | Project Closure, Review & Submission | 17-Feb-26 | 19-Feb-26 | Dolendra | Others | Completed | Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Unclear system architecture while defining RAG flow and module interaction. | Redesigned architecture diagram and validated end-to-end data flow from ingestion to dashboard.
Sprint 2 | Day 7 | Issues during data ingestion due to YouTube API quotas and rate limits. | Implemented request throttling and optimized ingestion logic with retry handling.
Sprint 3 | Day 11 | Inconsistent review formats causing preprocessing errors. | Standardized text cleaning pipeline and added validation checks.
Sprint 4 | Day 16 | Confusion in designing metadata schema for sentiment and aspect tagging. | Redefined metadata structure and aligned tagging format across modules.
Sprint 5 | Day 22 | Embedding generation latency and memory overhead on local machine. | Switched to lightweight sentence-transformer model and optimized batch size.
Sprint 6 | Day 24 | Pinecone index mismatch with metadata causing retrieval errors. | Rebuilt index and ensured correct index-to-docstore mapping; validated LangChain text splitter imports.
Sprint 7 | Day 30 | Groq LLM integration errors due to model version changes. | Updated model configuration and validated API integration with fallback handling.
Sprint 8 | Day 36 | React state and FastAPI CORS issues during UI integration. | Refactored API base URL handling and CORS; modularized dashboard components.
Sprint 9 | Day 40 | Build failure due to ESLint warnings and unused variables on Vercel. | Resolved ESLint issues and fixed setChatHistory reference; build passed with CI=true.
Sprint 10 | Day 45 | Render deploy: pandas build failed on Python 3.14; uvicorn could not find app. | Pinned Python to 3.12 via .python-version; changed start command to uvicorn dashboards.api_server:app.
Sprint 11 | Day 50 | ModuleNotFoundError: langchain.text_splitter on Render. | Added langchain-text-splitters and updated vector_store.py imports with try/except fallback.

## Retrospection
SL No. | Sprint No. | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 30-12-2025 | 02-01-2026 | Dolendra | Designing system architecture and defining RAG pipeline model. | Starting implementation without finalized architecture. | Structured documentation and modular planning. | Finalized end-to-end architecture from ingestion to dashboard.
2 | Sprint 2 | 02-01-2026 | 06-01-2026 | Dolendra | Building workflow and project goal definition with Lucidchart. | Ad-hoc task tracking without a backlog. | Keeping workflow diagrams updated. | Documented workflow and project goals.
3 | Sprint 3 | 06-01-2026 | 12-01-2026 | Dolendra | Collecting customer reviews from YouTube and centralizing raw data. | Manual copy-paste of review data. | Using API clients with rate limiting and retries. | Implemented ingestion pipeline and structured data storage.
4 | Sprint 4 | 12-01-2026 | 18-01-2026 | Dolendra | Cleaning and preprocessing raw review data with normalization. | Manual data cleaning without automation. | Improving preprocessing consistency and validation. | Standardized normalization and noise removal logic.
5 | Sprint 5 | 18-01-2026 | 24-01-2026 | Dolendra | Database design: Pinecone schema and embedding collection setup. | Hardcoding credentials and index names. | Using environment variables for all secrets. | Configured Pinecone index and embedding pipeline.
6 | Sprint 6 | 24-01-2026 | 28-01-2026 | Dolendra | Implementing LangChain retriever for contextually relevant reviews. | Using deprecated langchain.text_splitter without fallback. | Testing with langchain_text_splitters and community imports. | Integrated retriever and fixed text splitter imports for 0.2+.
7 | Sprint 7 | 28-01-2026 | 03-02-2026 | Dolendra | Content gap detection, alerts and report generation (PDF/Excel). | Hardcoding tagging rules without flexibility. | Testing tagging outputs iteratively. | Implemented alert service and report generator.
8 | Sprint 8 | 03-02-2026 | 10-02-2026 | Dolendra | UI integration: React dashboard and FastAPI query flow. | Mixing API base URL logic across components. | Using single REACT_APP_API_URL and CORS config. | Delivered React dashboard and FastAPI backend integration.
9 | Sprint 9 | 09-02-2026 | 12-02-2026 | Dolendra | Final testing and system integration; demo preparation. | Skipping CI-equivalent builds before deploy. | Running npm run build with CI=true before pushing. | Completed testing and demo readiness.
10 | Sprint 10 | 12-02-2026 | 16-02-2026 | Dolendra | System deployment (Vercel + Render), performance tuning. | Hardcoding file paths and Python version. | Using .python-version and correct uvicorn module path. | Refactored start command and Python version; deployed successfully.
11 | Sprint 11 | 16-02-2026 | 19-02-2026 | Dolendra | Full documentation (tech docs, architecture, API, UI) and handover. | Leaving deployment and import fixes undocumented. | Monitoring deployment logs and fixing errors. | Completed documentation and agile workflow artifacts.